## PAS 1-21-22
CAPSTONE PROJECT SCHEDULE OF ACTIVITIES
School Year 2021-2022
WEEK | CALENDAR DATE | EXAM/ ASSESSMENT | ACTIVITY | PURPOSE | TARGET DATE | DELIVERABLES
I. PROJECT PROPOSAL
1 | September 13-18 | Start of 1st Semester | 1. Orientation and Group Finalization | Final organization the Team and designate position to each member. | Before September 19 | 3 or 4 members per group
2 | September 20-25 |  | 2. Fine-tuning of working prototype; and review of proposal manuscript | Assess acceptability of the selected concept of proposal | before September 25 | Endorsed Project Proposal by PA to PC
3 | Sept 27-Oct 2 |  | 3. Start of Weekly consultation with PA, and Proposal endorsement and data gathering | Monintor the readiness status of the team for proposal defense | before October 2
4 | October 4-9 | PRELIM EXAMINATION (PROPOSAL DEFENSE) | 4. Mock proposal with PA, & Start of Proposal Defense | Approval of proposal concepts by Panelists; Endorsement for Final Defense by PA | Before October 30 | Approved of Project Proposal by PC, and prototype with at least 40-60% operational functionalities
5 | October 11-16 |  | 5. PROPOSAL DEFENSE
6 | October 18-23 |  | 6. Continuation of Proposal Defense; Start of system compliance; and Endorsement for Final Defense to PC by PA
7 | October 25-30
II. PROJECT CONSTRUCTION
8 | November 2-6 |  | 7. Revision of Chapters 1 to 3; Continuation of System Construction | Monitor the progress of project manuscript | Before November 6 | Revised Chapters 1 to 3, checked by PA
9 | November 8-13 | MIDTERM EXAMINATION | 8. Mock System Evaluation by PA; and Release of Final Defense Schedule | Track the progress of system development | before November 13 | system is 70% functional
10 | November 15-20 | System Evaluation/ System Dry-run | 9. System Testing and Evaluation by Practioner; Endorse for system dry-run and testing evaluation by Sponsor/ Benefactor; and Writing the draft of Chapters 4 and 5, and User's Manual; Start of Final Defense | Track the progress of developed system, and conduct assessment of the software quality by Practicioner; Track the progress of developed system and demonstrate the system to the project sponsor; and Track the progress of Chapters 4 to 5 and other documents | before November 27 | system is at least 90% functional; and Chapters 4-5, and Appendices
11 | November 22-27
12-13 | Nov 29-Dec 11 | SEMI-FINAL EXAMINATION (FINAL DEFENSE) | 10 FINAL DEFENSE | Approval of the Project Manuscript and system by the Panel of Evaluators | Before December 18 | the system is 100% functional and project documentation is 100% compliance
14 | December 13-18 |  | 11 FINAL RE-DEFENSE
15-16 | Dec 20 - 31 |  | 12. System updates of client's system requirements | Comply the system requirements | Before December 31 | system is 100% functional
17-18 | January 3-22 | FINAL EXAMINATION | 13 Proof Reading and Final Revision of the document; Evaluation of PA and PC; and Submission of Accomplishment Reports | Seek assistance of Grammarian for the final editing of Project Manuscript; and Assess individual participation and performance | before January 22 | the system is 100% functional; project documentation is 100% compliance and Signed Approval Sheet; Member's Accomplishment Report
19-20 | Jan 24 - 29 | SUBMISSION OF FINAL PROJECT (Submission of Hardbound copy) | 14 Submission of the Final Copy of the Project; Endorsement to Dean for compliance of CHED Requirements for graduation; and Release of Final Grades | Project documentation binding | before January 29 | Two (2) Hard bound copies of Project Manuscript (all pages and signatures are original); and softcopy of final manuscript (PDF Format)
| Prepared by: |  | Noted by:
| MAY S. CUAYCONG |  | DR. MAE B. LODANA
| Project Coordinator |  | Dean
2021-09-21
Conforme:
| ___________________________ |  | ______________________
| Project Manager |  | Project Adviser

## MONITORING
CAPSTONE PROJECTS DEVELOPMENT MONITORING
School Year 2021-2022
WEEK | CALENDAR DATE | EXAM/ ASSESSMENT | TARGET DATE | DELIVERABLES | STATUS/REMARKS
I. PROJECT PROPOSAL
1 | September 13-18 | Start of 1st Semester | Before September 19 | 3 or 4 members per group
2 | September 20-25 |  | September 20-October 9 | Endorsed Project Proposal by PA
3 | Sept 27-Oct 2
4 | October 4-9
5 | October 11-16 | PRELIM EXAMINATION (Proposal Defense) | Before October 30 | Approved of Project Proposal by PC, and prototype with at least 40% operational functionalities
6 | October 18-23
7 | October 25-30
II. PROJECT CONSTRUCTION
8 | November 2-6 |  | Before November 13 | Revised Chapters 1 to 3, checked by PA
9 | November 8-13
10 | November 15-20 | MIDTERM EXAMINATION | before November 20 | system is 70% functional
11 | November 22-27 | System Evaluation | Before December 4 | system is 90% functional
12 | Nov 29 - Dec 4
13 | December 6-11 | SEMI-FINAL EXAMINATION (System Dry-run) | before December 18 | checked Chapters 4-5, and Appendices by PA
14 | December 13-18
15 | December 20 - 25 |  | before December 31 | system is 100% functional
16 | December 27 - 31
17 | January 3-8 | FINAL EXAMINATION (Final Defense) | before January 22 | system is 100% functional and project documentation is 100% compliance
18 | January 10-15
19 | January 17-22
20 | January 24-29 | SUBMISSION OF FINAL PROJECT (Submission of Hardbound copy) | before January 29 | Signed Panel's Approval Sheet
21 | Jan 31 - Feb 5 |  | before February 5 | 1 Hard bound copy of Project Manuscript (all pages and signatures are original), softcopy of revised project